## Risk Matrix
5x5 TPRM Risk Assessment Matrix
Calculates Risk Rating based on Likelihood and Impact levels
Impact Of Occurrence
| Nominal (1) | Low (2) | Medium (3) | High (4) | Critical (5)
Critical | Moderate (5) | High (10) | High (15) | Critical (20) | Critical (25)
High | Moderate (4) | Moderate (8) | High (12) | High (16) | Critical (20)
Medium | Low (3) | Moderate (6) | Moderate (9) | High (12) | High (15)
Low | Low (2) | Low (4) | Moderate (6) | Moderate (8) | High (10)
Nominal | Nominal (1) | Low (2) | Low (3) | Moderate (4) | Moderate (5)

## Vendor Risk Assessments
THIRD-PARTY RISK & FINDINGS ASSESSMENT LOG
Evaluate inherent risk, findings, control breakdowns, and residual risk ratings aligned with organizational appetite.
NOTE ON CONTROLS: The "Controls / Due Diligence Findings" column here summarizes the outcome of a control assessment — it doesn't contain the assessment itself. The actual control review (the questionnaire, evidence
reviewed, and detailed scoring that produces this summary) happens during the Due Diligence stage — see the 2_DD folder for that process. This sheet only tracks how inherent risk moves to residual risk once that review is complete.
Vendor ID | Vendor / Third Party Name | Risk Category | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Rating | Controls / Due Diligence Findings | Finding Impact / Severity | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Rating | Remediation Status | Risk Acceptance / Action Plan
TP-001 | Acme Cloud Services | Cybersecurity | 5 | 5 | Critical | Lack of annual penetration testing report | High | 3 | 3 | Medium | In Progress | Vendor scheduled pen test for Q3.
TP-002 | Global Pay Solutions | Financial / PCI | 4 | 5 | Critical | Minor exception in SOC 1 user access control | Medium | 3 | 4 | High | Under Review | Remediation plan requested from vendor.
TP-003 | QuickDesign SaaS | Operational | 2 | 3 | Low | No formal DR plan for non-critical tool | Low | 1 | 2 | Low | Accepted | Risk accepted by Marketing VP.
TP-004
TP-005
TP-006
TP-007
TP-008
TP-009
TP-010
TP-011
TP-012
TP-013
TP-014
TP-015
TP-016
TP-017
TP-018
TP-019
TP-020